## Project Plan Template_2025
UK RACING PROJECT PLAN |  |  | PROJECT START | DURATION
| PROJECT TITLE |  | 2025-06-23 | 38 days | 130 hours | @ $45/hr
| UK Horse Racing |  | PROJECT END | REMAINING
|  |  | 2025-08-08 | -216 days
TASK # | TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION days | DURATION hours | COMMENTS | STATUS
1 | DATA PREPARATION | In Progress |  | 2025-06-23 | 2025-06-27 | 5 | 40 |  | Not Started
1.1 | Data familiarisation | Complete | Jon/Mike | 2025-06-23 | 2025-06-23 | 1 |  | Call with Mike for queries, especially about Ratings | In Progress
1.2 | Data preprocessing | Complete |  | 2025-06-24 | 2025-06-24 | 1 |  | Cleaning, formatting, missing values, storage | Complete
1.3 | Feature engineering + correlation matrix | Complete |  | 2025-07-14 | 2025-07-16 | 3 |  | Creating meaningful predictors for modelling | On Hold
1.4 | Initial benchmark model | In Progress |  | 2025-07-17 | 2025-07-20 | 4 |  | Multinomial logistic regression, to compare to main ML model
2 | PREDICTIVE MODEL (ML) | Not Started |  | 2025-06-30 | 2025-07-04 | 5 | 30
2.1 | Train and Test data split & ML model workflow | Not Started |  | 2025-06-30 | 2025-06-30 | 1 |  | Multinomial XGBoost model to be trialled
2.2 | Parameter tuning | Not Started |  | 2025-07-01 | 2025-07-02 | 2 |  | Timeframe depends on compexity of ML
2.3 | Model evaluation | Not Started |  | 2025-07-03 | 2025-07-03 | 1 |  | ML accuracy expcted to improve on benchmark model
2.4 | Initial model version | Not Started |  | 2025-07-04 | 2025-07-04 | 1 |  | Best ML trialled to-date (based on % accuracy at this stage)
3 | MARKET ANALYSIS | Not Started |  | 2025-08-25 | 2025-09-11 | 18 | 30
3.1 | Generate profit & loss reporting | Not Started |  | 2025-07-07 | 2025-07-07 | 1 |  | BSP, Fixed prices
3.2 | Generate "tree charts" to identify value segments | Not Started |  | 2025-07-08 | 2025-07-09 | 2 |  | e.g. what price/rating segment yields best ROI per recommendation
3.3 | Implement Kelly criterion as benchmark strategy | Not Started |  | 2025-07-10 | 2025-07-11 | 2 |  | Needs direct input/feedback from Mike
3.4 | Finalise value-based bet strategy | Not Started | Jon/Mike | 2025-07-10 | 2025-07-11 | 2 |  | Needs direct input/feedback from Mike
4 | RACEDAY DEPLOYMENT | Not Started |  | 2025-07-14 | 2025-07-18 | 5 | 20
4.1 | Send model object to developer for production | In Progress | Jon/Developer | 2025-07-14 | 2025-07-14 | 1 |  | RDS file (includes bet strategy)
4.2 | Reconcile raceday data & recommendations back to modelling | In Progress |  | 2025-07-15 | 2025-07-16 | 2 |  | Ensure live recommendations mimic modelling
4.3 | Additional Model iterations given any anomialies in production | In Progress |  | 2025-07-17 | 2025-07-18 | 2
4.4
5 | LIVE TESTING/PRODUCTION | Not Started |  | 2025-07-21 | 2025-07-25 | 5 | 10
5.1 | Finalise model production and pipeline | In Progress | Jon/Developer | 2025-07-21 | 2025-07-21 | 1
5.2 | Live testing | Not Started | Jon/Mike/Developer | 2025-07-22 | 2025-07-24 | 3
5.3 | Live production | Not Started | Jon/Mike/Developer | 2025-07-25 | 2025-07-25 | 1
5.4
1575
Formulas:
DURATION = [PROJECT START]-TODAY() & " days"

## Project Plan Template_2026
UK RACING PROJECT PLAN |  |  | PROJECT START | DURATION
| PROJECT TITLE |  | 2026-02-01 | 74 days | 65 hours | @ $45/hr | 1800
| UK HORSE RACING |  | PROJECT END | REMAINING
|  |  | 2026-04-15 | 34 days
TASK # | TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION days | DURATION hours | COMMENTS | STATUS
1 | MODEL v2 FINAL VALIDATION | In Progress |  | 2026-02-01 | 2026-02-28 | 28 | 15 |  | Not Started
1.1 | Regular iterations/tuning | In Progress |  | 2026-02-01 | 2026-02-28 | 28 |  | e.g. goingofficial feature added over "going" | In Progress
1.2 | Testing results on recent races | In Progress |  | 2026-02-01 | 2026-02-28 | 28 |  | Ensuring model profitability is sustained | Complete
1.3 | Prepare final model object for live recommendation | In Progress | Burat/Jon | 2026-02-28 | 2026-02-28 | 1 |  | Mappoing training data for Burat etc | On Hold
1.4 | Finalising bet criteria | In Progress | Burat/Jon | 2026-02-25 | 2026-02-28 | 4 |  | Live rules for betting (e.g. 999 TF rating = NO BET)
1.5 | Model implementation | In Progress | Burat |  |  |  |  | Timing TBD (Burat/JS to reconcile live race recommendations)
2 | MODEL v3 PREPARATION | Not Started |  | 2026-03-01 | 2026-03-31 | 31 | 25
2.1 | Additional features - jockey/trainer ratings | On Hold |  | 2026-03-01 | 2026-03-15 | 15 |  | Commenced but needs further dicussion
2.2 | Additional features - bookie prices (flucs) | Not Started |  | 2026-03-16 | 2026-03-31 | 16 |  | Should be simple to include as model feature OR in bet strategy
2.3 | Investigate class-specific models | On Hold |  | 2026-03-16 | 2026-03-31 | 16 |  | A separate model for C1 races for example
2.4 | Model tuning/validation | Not Started |  | 2026-03-16 | 2026-03-31 | 16 |  | Model object to Burat before 1st April
2.5 | Model accuracy/profitability reporting | Not Started |  | 2026-03-16 | 2026-03-31 | 16
3 | v3 LIVE TESTING/PRODUCTION | Not Started |  | 2026-04-01 | 2026-04-15 | 15 | 25
3.1 | Betfair Automation | Not Started | Mike/Jon | 2026-04-01 | 2026-04-15 | 15 |  | Discuss timing with Mike
3.2 | Optimise model production and pipeline | Not Started |  | 2026-04-01 | 2026-04-15 | 15 |  | Ensure market data is real-time (mimicing training data timing)
3.3 | Live testing | Not Started |  | 2026-04-01 | 2026-04-15 | 15 |  | Paper trading and results comparison to testing
3.4 | Live production | Not Started |  | 2026-04-01 | 2026-04-15 | 15 |  | Timing/approcach to be discussed
4 | NATIONAL HUNT MODEL v1 | Not Started
4.1 | TBD | Not Started
4.2 |  | Not Started
4.3 |  | Not Started
4.4
5 |  | Not Started
5.1 |  | Not Started
5.2 |  | Not Started
5.3 |  | Not Started
5.4
1575
Formulas:
DURATION = [PROJECT START]-TODAY() & " days"